## NRRI
Project name | Project status | Project web site url | Theme | Main contact forename | Main contact surname | Main contact organisation | Contact organisation url | Partner organisations | Parent project | Multi-site | Project picture | Picture description | Project summary | Monitoring surveys and results | Lessons learnt | Country | River basin district | River basin | River name | Subcatchment area category | Subcatchment area | Subcatchment maximum altitude category | Subcatchment maximum altitude | Subcatchment dominant geology | Ecoregion | Subcatchment dominant land cover | Subcatchment waterbody ID | Site name | WFD water body code | WFD water body name | WFD national typology | Pre-project morphology | Reference morphology | Desired post project morphology | Heavily modified water body | Site designation | Local site designation | Protected species present | Invasive species present | Species of interest | Dominant hydrology | Dominant substrate | River corridor land use | Average channel width category | Average channel width | Average channel depth category | Average channel depth | Mean discharge category | Mean discharge | Average channel gradient category | Average channel gradient | Average unit stream power | Reach length affected | Project started | Works started | Works completed | Project completed | Total cost category | Total cost | Benefit to cost ratio | Funding source | Investigation and design cost category | Investigation and design cost | Investigation and design lead organisation | Investigation and design contact forename | Investigation and design contact surname | Stakeholder engagement cost category | Stakeholder engagement cost | Stakeholder engagement lead organisation | Stakeholder engagement contact forename | Stakeholder engagement contact surname | Works and supervision cost category | Works and supervision cost | Works and supervision lead organisation | Works and supervision contact forename | Works and supervision contact surname | Post-project management and maintenance cost category | Post-project management and maintenance cost | Post-project management and maintenance lead organisation | Post-project management and maintenance contact forename | Post-project management and maintenance contact surname | Supplementary funding information | Monitoring cost category | Monitoring cost | Monitoring lead organisation | Monitoring contact forename | Monitoring contact surname | Specific mitigation motivation | Hydromorphological quality motivation | Biological quality motivation | Physico-chemical quality motivation | Other motivation | Bank and bed modifications measure | River corridor measure | Channel pattern measure | Other technical measure | Management interventions | Social measure | Wider engagement measure | Biological quality element monitored | Biological quality element data | Hydromorphological quality element monitored | Hydromorphological quality element data | Physico-chemical quality element monitored | Physico-chemical quality element data | Other response monitored | Other quality element data | Monitoring document | Monitoring document description | Image gallery image | Image gallery image description | Additional document | Additional document description | Additional link | Additional link description | Supplementary information | Data originating from | Grid reference | Total Cost (£) | County | Floodplain soils | River type | River bed gradient | Cumecs 1_100 | Cumecs bankfull | Cumecs normal low | WFD water body status | WFD habitat quality | WFD water quality constraints: Y/N | WFD water quality constraints: comments | WFD programme of measures: Y/N | Objectives type 1 - PRIMARY | Objectives type 1 - SECONDARY | Objectives type 1 - MINOR | Objectives type 1 - other | Objectives type 2 - PRIMARY | Objectives type 2 - SECONDARY | Objectives type 2 - MINOR | Objectives type 2 - other | Objectives type 3 - PRIMARY | Objectives type 3 - SECONDARY | Objectives type 3 - MINOR | Objectives type 3 - other | Objectives type 4 - key activities | Objectives type 5 | Catchment geology - detail | RRC comments documentation details | Additional cost information | Driver - BAP Biodiversity Action Plan | Driver - HD | Driver - SSSI | Driver - WFD | Driver - CCA | Driver - Other
Darent River Project - Kent | Completed (monitoring) | 0 | 0 | John | Cave | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Objectives: To construct artificial springs along the river banks to augment flows, reduce amount of abstraction. Encourage fish back to river. Local description: Designated one of the 40 worst low flow rivers in UK. Joint NRA Thames Water project. work scheduled for 1994. Main motivation: Fisheries, , | 0 | 0 | England | Southern, Kent & East Sussex | Darent | Darent | 0 | 0 | 0 | 0 | Calcareous (Chalk) | 0 | Mixed (urban and rural) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1012 | 0 | 0 | 2004-01-01 | 2004-01-01 | 0 | 0 | 0 | Environment Agency (+SEPA), | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Options for rehabilitation and enhancement - River Darent (June 2004) - filed in RRC reports | 0 | 0 | 0 | Old NRRI (FileMaker) | TQ545733 | 0 | Kent | Lome / Clay | Chalk Stream - Lowland | 0 | 0 | 0 | 0 | 0 | 0 | No | 0 | 0 | 0 | 0 | 0 | - construction of artificial springs | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hermitage Stream Restoration Project | Completed (no monitoring) | 0 | 0 | Lawrence | Talks | Environment Agency | 0 | Havant Council | 0 | 0 | 0 | 0 | Objectives: The aims of the rehabilitation project were to: - ensure that the existing level of flood defence was maintained; - restore/improve the stream to a more natural river environment; - create a green and pleasant place for all to enjoy for recreation, amenity, education and wildlife; - carry out the works within a previously identified 1.5 kilometre stretch of the stream Additionally, in 2006, sources of pollution were identified, for example plumbing was fixed in a number of homes. Local description: Located in Leigh Park . Straightened and lined with concrete during previous flood protection scheme. Damaged by fly-tipping and pollution. Main motivation: Habitat, Landscape, Pollution mitigation, Flood defence, , | 0 | March 2003. Mostly worked well but donwstream section still has shopping trolleys etc. Appears that some of the work has either eroded away through high flows or may be due to local vandals. | England | Southern, Solent & South Downs | Hermitage Stream | Drains into Solent at Langstone Harbour | 0 | 0 | 0 | 0 | Calcareous (Chalk) | 0 | Urban (housing) | GB107042016370 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1000 | 1999-01-01 | 1999-01-01 | 1999-01-01 | 1999-01-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | EA Site leaflets and letter from Lawrence Talks filed in ‘Non RRC Projects’ filing cabinet under H - ‘Hermitage Stream restoration project’ Hermitage Stream Restoration Project (Havant) - filed in electronic reference material (044) | 0 | 0 | 0 | Old NRRI (FileMaker) | SU708077 | 0 | Hampshire | Loam / Clay | 0 | 0 | 0 | 0 | 0 | Moderate | Moderate | No | 0 | Programme of measures | 1.8 Bank reprofiling to restore lost habitat type and structure/armouring removed | 1.15 Artificial bed/bank removal and replaced by softer material (>100m) 1.16 Establishment of vegetation for structure/revetment (e.g., use of willows) 1.20 Aquatic/marginal planting | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
River Ravensbourne (east branch) Rehabilitation Scheme | Completed (monitoring) | 0 | 0 | Richard | Copas | Environment Agency | 0 | 0 | 0 | 0 | 0 | 0 | Objectives: Objectives: Recreate a sinuous channel with narrow flow width, low berms and shallow slopes, improve flow diversity with riffles and pools, improve visual appearance of the brook, increase habitat for invertebrates and fish, to improve other areas of the golf course. Work undertaken: Phase 1 (Upstream culvert to elm grove) - Culvert face dressed with blockstone. Banks and beds re-profiled to form pool. Gravel placed in channel. Phase 2 & 3 (Elm grove to downstream culvert) - Banks pulled back to form two-stage channel profile. Edges protected by hazel spiling. Low flow channel excavated, with deeper pools and riffles, covered with imported gravel. Vegetation planting. Local description: Located on Bromley Common Golf Course. River had been straightened and severly maintained as a steep sided drain. River isolated from floodplain. Bed and banks consisted of well concreted rounded gravel. Main motivation: Habitat, Landscape, , , | Contract documents Photographs pre-works Photographs post-works Audits | The low flow channels developed well. Early colonisers caused a minor flooding problem by covering the channel, then being swept downstream to block the culvert grills. Vegetation growth has continued to narrow the channel, creating greater flow diversity. The berms have accreted silt and are developing more of a terrestrial community, this has concentrated flows and enhanced the low flow channel. The downstream pool designed to trap sediment has also developed a good wetland habitat. The banks have vegetated well with low maintenance grass and flowers and have not been covered by rank vegetation due to the removal of top soil. The plug planted flowers have not taken. | England | Thames, Southeast | Thames | Ravensbourne: Bromley Common Golf Course, Southborough, Bromley | 0 | 0 | 0 | 0 | Calcareous (Chalk) | 0 | Urban (parkland) | GB106039023260 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Flashy | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1500 | 1993-01-01 | 1993-01-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 'Audit of 20 Rehabilitation Projects' Environment Agency - Thames Region, 1998 - filed in manuals | 0 | 0 | 0 | Old NRRI (FileMaker) | TQ424669 | 36000 | London | Loam / Sand | Lowland Clay - Lowland | 1:400 | 0 | 0.44 | 0 | Poor | Poor | Yes | Poor, due to urban surroundings and periodic foul water inputs | 0 | 1.8 Bank reprofiling to restore lost habitat type and structure/armouring removed 1.4 X-sectional habitat enhancement (>500) - two-stage channel profiles etc. 1.14 Tree/shrub planting along bankside (only if covers >500m of bank or >0.5ha) 1.16 Establishment of vegetation for structure/revetment (e.g., use of willows) | 1.13 Sand, gravel and other sediment traps to benefit wildlife | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | The Ravensbourne rises as Chalk springs (in Holwood Park; dry valleys extend into the North Downs). The lower catchment is mainly impervious Eocene deposits. | Ivertebrate survey - pre and post scheme | 0
River Cole - Sevenhampton | Completed (monitoring) | 0 | 0 | Graham | Scholey | Environment Agency | 0 | 0 | 0 | 0 | 0 | 0 | Objectives: Objectives: Increase turbulence using riffles to provide silt-free spawning areas, invertebrate habitat and stimulate re-oxygenation. Create pools for fish shelter, improve in-channel and bankside diversity, create a wetland feature fed by the out of bank river. Work undertaken: - Bank re-profiling at four sections - Provision of pool/riffle structures - Flow deflectors - Wetland scrape Local description: Reach exhibited eroding/slumping banks where no tree or shrub cover was available. Sluggish over-wide channel with low flow summer water. Lack of in-stream habitat. Flash floods causing landowner to loose sheep. Main motivation: Fisheries, Habitat, , , | Photographs post-works Pre-project data: specify above Audits | The in-channel enhancement works have improved flow diversity, especially at low-flow which was the main concern. The replacement of spawning gravels has not worked as well as expected, they remained largely silty or have been displaced. The re-profiling has increased bankside diversity, and has addressed the farmers concern over sheep loss, but not increased wetland plant diversity significantly other than at one of the ledges. The wetland scrape has proved the most successful. It is also the most valuable since good wetland habitat in this part of the Cole catchment is very rare. | England | Thames, West | Thames | Cole: Roves Farm, Sevenhampton | 0 | 0 | 0 | 0 | Calcareous (Chalk) | 0 | Rural (arable) | GB106039022900 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Flashy | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 250 | 1992-01-01 | 1992-01-01 | 1992-01-01 | 1992-01-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Audit of 20 Rehabilitation Projects' Environment Agency - Thames Region, 1998 - filed in manuals | 0 | 0 | 0 | Old NRRI (FileMaker) | SU218874 | 13500 | Wiltshire | Loam / Clay | Lowland Clay - Lowland | 0 | 0 | 8.3 | 0 | Moderate | Moderate | No | 0 | 0 | 1.8 Bank reprofiling to restore lost habitat type and structure/armouring removed 1.12 Current deflectors/concentrators to create habitat and flow diversity 1.5 Long section habitat enhancement (>500m) - pool/riffle sequences etc. restored | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.13 Other (scrape in drying reedbed) | 0 | 0 | 0 | 0 | Chalk scarp headwaters but catchment is largely low-lying and impervious (clay). | 0 | 0
Gatwick Stream - Weir bypass via Grattons Park Ditch | Completed (monitoring) | 0 | 0 | Dave | Webb | Environment Agency | 0 | 0 | 0 | 0 | 0 | 0 | Objectives: Objectives: To restore fish passage between the lower section and headwaters, marginal in-stream habitat creation, reduce bank disturbance and retain terrestrial habitat. Work undertaken: - Connection made at upstream end, designed to throttle flow in high flow conditions. - Ditch dredged by up to 1m, uncovering gravel bed - Banks pulled back in places - At downstream end, reconnection to Gatwick Stream through a section of previously cut off meanders. - Gradient was varied in ditch to produce pools and enable gravel riffles to be introduced Local description: Flood defence modifications in the 1950s. Stream concrete lined to control overspill, weirs added to retain levels and control erosion. fishery value poor. Main motivation: Fisheries, Habitat, , Barrier mitigation, Morphology | Photographs post-works Photographs pre-works Fisheries survey Audits RHS RCS | The works have achieved the objectives in terms of additional habitat creation, and retention/minimal disturbance of the surrounding terrestrial habitat. A fisheries survey of the ditch has not taken place, but informal surveys suggest populations of bullhead, brook lamprey and native brown trout use or inhabit the new ditch. | England | Thames, Southeast | Thames | Gatwick Stream - Gratton Park Ditch, Grattons Park | 0 | 0 | 0 | 0 | Siliceous (Igneous & Sand) | 0 | Rural (mixed) | GB106039017500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Flashy | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 500 | 1996-01-01 | 1996-01-01 | 1996-01-01 | 1996-01-01 | 0 | 0 | 0 | Environment Agency (+SEPA), | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Audit of 20 Rehabilitation Projects' Environment Agency - Thames Region, 1998 - filed in manuals | 0 | 0 | 0 | Old NRRI (FileMaker) | TQ289382 | 28000 | W Sussex | Loam | 0 | 0 | 0 | 0 | 0 | Moderate | Moderate | No | was very poor, but has improved since late 80’s. | 0 | 1.4 X-sectional habitat enhancement (>500) - two-stage channel profiles etc. | 0 | 0 | 0 | 2.3 Obstructing structure modified/removed to enable fish migration | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | mixed - sand with clay and gravels | 0 | 0
River Dun Habitat - Froxfield | Completed (monitoring) | 0 | 0 | Graham | Scholey | Environment Agency | 0 | 0 | 0 | 0 | 0 | 0 | Objectives: Objectives: Remove impoundments, reinstate the original gravel beds, pools and riffles to improve fishery, define a much narrowed channel, enhance in-channel and bankside diversity through re-profiling, ledge creation. Work undertaken: Section A: Small stone groynes used to promote pool scour and narrow left bank. Narrowing on right bank by using 300mm larch and willow logs. Small parts of section revetted with stone. Section B: A new sinuous channel was defined with a hard edge, using hazel hurdles on the left and stone on the right. Width was returned to 5m. Impoundment was removed and replaced with two low rock chutes. Several submerged deflectors were added. Section C: Various narrowing works on both banks, using willow hurdles and blockstone. Local description: Identified as needing enhancement by fisheries. Ponded section formed by home made corrugated iron and post weirs - used as a duck feeding pond. Ducks causing bare banks and bank erosion. Stream bed heavily silted, pond feeding poor quality water into the reach. Main motivation: Bank erosion, Bank erosion, Fisheries, Habitat, , Barrier mitigation, Morphology | Job Specification Stated Objectives Audits Photographs pre-works Photographs post-works | Removal of impoundments and new channel works have narrowed the stream and re-exposed original gravel bed. Some marginal aquatic vegetation has established on wet ledges, the more regimented hurdles have not been so successful. | England | Thames, West | Thames | Dun, Kennett (North Standen Estate, Froxfield, nr. Hungerford) | 0 | 0 | 0 | 0 | Calcareous (Chalk) | 0 | Rural (arable) | GB106039017390 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Steady | Gravel | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 200 | 1995-01-01 | 1995-01-01 | 1995-01-01 | 1995-01-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Audit of 20 Rehabilitation Projects' Environment Agency - Thames Region, 1998 - filed in manuals | 0 | 0 | 0 | Old NRRI (FileMaker) | SU314680 | 24000 | Berkshire | Lome / Chalk | Chalk Stream - Mid altitude | Good | 0 | 2.1 | 0 | Moderate | Moderate | No | Water quality generally good | 0 | 1.6 River narrowing due to depleted flows or previous over-widening 1.8 Bank reprofiling to restore lost habitat type and structure/armouring removed 1.11 Fish cover established by other means | 1.20 Aquatic/marginal planting | 0 | 0 | 2.3 Obstructing structure modified/removed to enable fish migration | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Chalk valley | 0 | EH (Thames West) also a listed contact according to an spreadsheet of fisheries projects June 2010. Landowner - North Standen Estate Ltd. 5 West Mills. Newbury. Berks. P Magor 0635522088/ I Talbot 01488682895.
River Pool Enhancement Scheme - Catford | Completed (monitoring) | 0 | 0 | Richard | Copas | Environment Agency | 0 | 0 | 0 | 0 | 0 | 0 | Objectives: Objectives: Fisheries improvement in terms of flow diversity, edge habitat and shelter, general habitat enhancement, increase the visual and amenity value of the site. Methods: - Rotten wood toe boarding removed on 650m reach to encourage marginal vegetation growth - Blockstone deflectors instaleld - Large stepping stones placed in river to create turbulence - Three under bank fish shelters created (£3000 each) - Invasive plants removed - Two damp bankside bays were cut into the slope and planted with goat willow to add diversity to the bank profile Local description: Heavily engineered and straightended in 1960s which had severly degraded the in-channel habitat. Little in-stream or marginal vegetation, large concrete crump weir proving to be barrier to fish. Main motivation: Fisheries, Habitat, Landscape, , , | Job specification Contract documents Photographs pre-works Photographs post-works Fisheries survey Audits | Toe board removal and associated planting has developed well, but slower than expected. Hurdle planting and narrowing has not been successful, with erosion occurring faster than vegetation growth, leaving shallow puddles behind the proud posts. Deflectors have had a varied effect. The largest has accreted a 5m shoal. Smaller deflectors are having less of an effect. The scattered blocks received a mixed review. They were seen as litter collectors and a possible flood defence problem. Fish shelters have remained free from sediment accretion, and have not been damaged. Fisheries staff have indicated that the scheme and stocking were progressing well, until a large pollution incident wiped out the fish population. Knotweed and Basalm remain a problem. | England | Thames, Southeast | Thames | Pool, Ravensbourne (South of Lewisham, Catford) | 0 | 0 | 0 | 0 | Calcareous (Chalk) | 0 | Urban (mixed) | GB106039023250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Flashy | Gravel | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 650 | 1994-01-01 | 1994-01-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Audit of 20 Rehabilitation Projects Environment Agency - Thames Region, 1998 - filed in manuals | 0 | 0 | 0 | Old NRRI (FileMaker) | TQ371724 | 42600 | London | Loam / Clay | Lowland Clay - Lowland | low | 0 | 0 | 0 | Moderate | Moderate | Yes | Very poor, is a limiting factor | 0 | 1.20 Aquatic/marginal planting 1.17 Eradication of alien species 1.16 Establishment of vegetation for structure/revetment (e.g., use of willows) 1.12 Current deflectors/concentrators to create habitat and flow diversity | 1.18 Provision of habitat especially for individual species - otter, kingfisher etc. 1.4 X-sectional habitat enhancement (>500) - two-stage channel profiles etc. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Invertebrate survey: post scheme Fisheries surveys: 1991, 1994, 1996 | 0
Kyd Brook Deculverting - Sundridge Park Golf Course | Completed (monitoring) | 0 | 0 | Richard | Copas | Environment Agency | 0 | 0 | 0 | 0 | 0 | 0 | Objectives: Objectives: Alleviate flooding of the golf course, reduce a health and safety hazard, enhance the landscape and habitat value of the brook. De-culverting. Work undertaken: - 370m section re-routed away from culvert into an open channel - redundant culvert filled with pulverised fuel ash/cement grout to prevent further collapse - banks supported using dead hazel spiling to just above water level - outside of bends revetted with tanalised larch posts and spiled willow withies to prevent erosion occuring. Local description: Park landscape of significant historic interest. Flooding of golf course has occurred - attributable to increased rate and volume of run-off from urban development and because of age of culverted section collapses were common causing blockages. Health and safety issue associated with the subsidence. Main motivation: Bank erosion, Bank erosion, Flood defence, Habitat, , , | Job specification Photographs post-works Photographs pre-works Audits | The work has been a success in terms of the objectives; opening the channel, alleviating a safety problem and reducing flood risk. The final result could have been more sensitive to environmental considerations, given more support by the landowner in both the design and the subsequent management of the site. | England | Thames, Southeast | Thames | Kyd Brook, Quaggy, Ravensbourne. In Sundridge Park Golf Course. (The Kyd Brook is an alternative name for the part of the Quaggy that flows through Chislehurst). | 0 | 0 | 0 | 0 | Calcareous (Chalk) | 0 | Urban (mixed) | GB106039023260 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Flashy | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 370 | 1995-01-01 | 1995-01-01 | 1996-01-01 | 1996-01-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Audit of 20 Rehabilitation Projects' Environment Agency - Thames Region, 1998 - filed in manuals | 0 | 0 | 0 | Old NRRI (FileMaker) | TQ418707 | 200000 | London | Loam / Clay | Lowland Clay - Lowland | 1:300 | 0 | 0 | 0 | Poor | Poor | No | 0 | 0 | 1.2 Reach remeandered (<500m) 1.4 X-sectional habitat enhancement (>500) - two-stage channel profiles etc. | 1.12 Current deflectors/concentrators to create habitat and flow diversity 1.16 Establishment of vegetation for structure/revetment (e.g., use of willows) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Terrestrial gravels and sand | 0 | 0
Tidal River Crane Enhancement - Twickenham | Completed (monitoring) | 0 | 0 | Richard | Copas | Environment Agency | 0 | 0 | 0 | 0 | 0 | 0 | Objectives: Objectives: Landscaping to introduce variety to the vertical profile. Utilisation of a range of different materials to minimise the linearity of the defences, integrate vegetation into the works and retain existing mature trees. Work undertaken: - Pile Screens to provide protection. - Landform work: creating low level raised ledges, constructing mooring platforms, created high level planted ledges - Landscape work: vegetation planting - Importing of gravel onto river bed Local description: Area known to be at risk of flooding. Tidal flood defences badly deteriorated. Capital flood defence works to be followed by landscaping. Main motivation: Landscape, Flood defence, Navigation, | Photographs post-works Contract documents Audits | The overall objective, to renew the tidal flood defences incorporating a range of benefits associated with the soft engineering and landscape works, was achieved. | England | Thames, Northeast | Thames | Crane (upstream of Richmond Lock) | 0 | 0 | 0 | 0 | Calcareous (Chalk) | 0 | Urban (mixed) | GB106039023030 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Flashy | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 250 | 1993-01-01 | 1993-01-01 | 1997-01-01 | 1997-01-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Audit of 20 Rehabilitation Projects' Environment Agency - Thames Region, 1998 - filed in manuals | 0 | 0 | 0 | Old NRRI (FileMaker) | TQ166754 | 50000 | London | Loam / Sand | Lowland Clay - Lowland | 1:1400 (1:500 at upstream and downstream limits) | 0 | 4.8 | 0 | Good | Good | No | 0 | Programme of measures | 1.20 Aquatic/marginal planting 1.14 Tree/shrub planting along bankside (only if covers >500m of bank or >0.5ha) 1.16 Establishment of vegetation for structure/revetment (e.g., use of willows) | 0 | 0 | - reprofiling to reduce flood risk | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | A flat, generally impervious (mostly London Clay) catchment of suburban character. | 0 | 0
River Windrush Enhancement Works at Worsham | Completed (monitoring) | 0 | 0 | Graham | Scholey | Environment Agency | 0 | 0 | 0 | 0 | 0 | 0 | Objectives: Objectives: Increase summer flow velocities to prevent excessive siltation and reed growth, re-create the natural gravel bed, increase spawning sites, increase in-channel and edge habitat diversity. Work undertaken: - Channel narrowing: A 500m length was narrowed by up to 60% along the right bank, with a varied edge line (average new width was 4.5m). - Coir fibre and larch posts: Designed to last 5 to 8 years, allowing the fill material and plant root systems to bind together and form new bank and edge. - Blockstone: Two layers of blockstone were used to create a retaining wall. - Gravel introduction: 500 tonnes of angular flint rejects were broadcast into the narrow reach to recreate a gravel bed. - Spawning weir: Special spawning weir was designed to provide spawning conditions. Local description: Windrush has been subject tof various land drainage schemes. Land use mainly sheep farming, causing problems in terms of bank poaching and erosion. Channel is over-wide. Low flows and low velocities causing accelerated siltation and encroachment of emergent vegetation. Main motivation: Bank erosion, Bank erosion, Fisheries, Habitat, , , | Photographs post-works Photographs pre-works Audits | The narrowing works have prevented the deposition/accretion of silts and the associated re-colonisation by emergents, by increasing low-flow velocities. This has also kept clean the gravel bed that has, in conjunction with the variable width, sorted into a pool/riffle profile. The two weirs have created spawning areas which are being used by both coarse fish and trout. | England | Thames, West | Thames | Windrush (d/s of Worsham, nr Minster Lovell) | 0 | 0 | 0 | 0 | Calcareous (Chalk) | 0 | Rural (parsture) | GB106039030440 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Flashy | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1600 | 1992-01-01 | 1992-01-01 | 1993-01-01 | 1993-01-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Audit of 20 Rehabilitation Projects' Environment Agency - Thames Region, 1998 - filed in manuals | 0 | 0 | 0 | Old NRRI (FileMaker) | SP300105 | 42000 | Oxfordshire | Clay / Alluvium | 0 | sufficient to keep many gravel beds clean | 0 | 0 | 0 | Moderate | Good | No | Very good - GQA grade A | Programme of measures | 1.6 River narrowing due to depleted flows or previous over-widening 1.16 Establishment of vegetation for structure/revetment (e.g., use of willows) 1.10 Gravel and other sediments imported/managed for habitat enhancement | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | A predominantly pervious (68% Oolitic Limestone) catchment on the dip-slope of the Cotswolds. | 0 | 0
Information on over 4,000 other projects is available to RRC Members
The NRRI has a lot of sources, because of this, there gaps in fields that are unique to particular data sources.
Please note that we cannot send you all of the information available, the RRC will determine the information that is most relevent to your ennquiry.